## Summary
EdgeCipline — Pre-Launch Verification
Web first (W1–W6), then Android (A1–A3). Any F in W1–W3 or A1–A2 = do not launch.
Section | Total | Pass | Fail | Not done | Status
W1. Production config — read before you click
W2. Lockout paths — if these break, nobody can get in
W3. Money — irreversible if wrong
W4. Core loop on web
W5. Support is reachable — your post-launch safety net
W6. Admin sanity
A1. Store compliance — suspension risk
A2. Google Play money
A3. App-only behaviour
Before deploy
LAUNCH DECISION
Rollback build / tag:
Signed off by / date:

## Checklist
# | Pass | Section | Test | Expected result | Result | Tested by | Date | Notes / bug link
Pass 1 — Web › W1. Production config — read before you click
1 | Pass 1 — Web | W1. Production config — read before you click | Backend .env (prod): Razorpay key is LIVE (not rzp_test_), MONGO_URI is the production cluster and MONGO_URI_LOCAL is NOT set, Cloudinary is the production account, mail provider is production, SUPPORT_TICKETS_ENABLED=true, free-trade limit enforcement is on.
2 | Pass 1 — Web | W1. Production config — read before you click | Web build flags: NEXT_PUBLIC_PAYMENTS_ENABLED=true, NEXT_PUBLIC_PLAY_BILLING_ENABLED=false, NEXT_PUBLIC_RAZORPAY_KEY_ID is the live key | Confirm the checkout modal does NOT say "Sandbox demo".
3 | Pass 1 — Web | W1. Production config — read before you click | CORS: allowlist contains only the production frontend origin(s) | No localhost, no old Cloudflare preview URLs. CORS_DEBUG off.
4 | Pass 1 — Web | W1. Production config — read before you click | Secrets: JWT / admin JWT secrets differ from staging/dev and are not committed to git.
5 | Pass 1 — Web | W1. Production config — read before you click | HTTPS: site and API load over HTTPS; browser console shows no mixed-content or CORS errors on the dashboard.
6 | Pass 1 — Web | W1. Production config — read before you click | Database backup: Atlas (or host) shows automated backups enabled and at least one snapshot exists.
7 | Pass 1 — Web | W1. Production config — read before you click | Indexes & seeds: syncIndexes.js run once on production; production admin exists (ensureAdminUser.js --list); knowledge base seeded (/support shows articles, not "Guides are on their way").
Pass 1 — Web › W2. Lockout paths — if these break, nobody can get in
8 | Pass 1 — Web | W2. Lockout paths — if these break, nobody can get in | Register → OTP. Register a fresh email | OTP email arrives within a minute from the production mail provider; correct OTP works; wrong OTP rejected; resend works.
9 | Pass 1 — Web | W2. Lockout paths — if these break, nobody can get in | Accept terms | New account is asked to accept Terms once, then never again.
10 | Pass 1 — Web | W2. Lockout paths — if these break, nobody can get in | Login / session / logout | Login works; refresh keeps you in; open a second tab → still logged in; logout in one tab logs out the other.
11 | Pass 1 — Web | W2. Lockout paths — if these break, nobody can get in | Forgot password | Request reset → email arrives → link opens /reset-password → new password works, old one does not, the link cannot be reused.
12 | Pass 1 — Web | W2. Lockout paths — if these break, nobody can get in | Admin login. /admin/login with the real production admin (not the local seed) | admin dashboard loads; wrong password rejected. (3 failures lock for 1 hour.)
13 | Pass 1 — Web | W2. Lockout paths — if these break, nobody can get in | Admin routes blocked for users. Logged in as a normal user, open /admin/users directly | refused, not rendered.
Pass 1 — Web › W3. Money — irreversible if wrong
14 | Pass 1 — Web | W3. Money — irreversible if wrong | Real Razorpay payment. Buy the cheapest plan with a real card/UPI on the LIVE key | Premium unlocks immediately without a refresh; Settings shows plan + correct expiry; payment appears in /admin/payments with the same order id and amount as the Razorpay dashboard.
15 | Pass 1 — Web | W3. Money — irreversible if wrong | Payment failure. Start checkout and cancel / use a failing method | clear error, still free plan, no charge, retry works without a duplicate order.
16 | Pass 1 — Web | W3. Money — irreversible if wrong | Pricing matches | Plan cards on the paywall, the amount on the pay button, and what Razorpay actually charged are the same numbers (monthly / 3-month / 6-month).
17 | Pass 1 — Web | W3. Money — irreversible if wrong | Coupon (if you launch with one) | Valid code reduces the payable amount on the button and the charged amount matches; invalid/disabled code shows "This code isn't valid".
18 | Pass 1 — Web | W3. Money — irreversible if wrong | Premium survives re-login | Log out and back in → still Premium.
Pass 1 — Web › W4. Core loop on web
19 | Pass 1 — Web | W4. Core loop on web | Onboarding | New account → onboarding → create a setup → lands on the dashboard; Growth Path shows "Build Setup" as done.
20 | Pass 1 — Web | W4. Core loop on web | Manual trade — Forex. Log one trade filling Setup / Pattern, SL/TP, R:R, mood, confidence, emotions | saves; appears in Trades; detail/edit shows every field intact.
21 | Pass 1 — Web | W4. Core loop on web | Manual trade — Indian (Options + Equity). Switch to India market, log one of each | strike/CE-PE (options) or symbol/qty (equity), SL/TP, trade type, screenshot all saved.
22 | Pass 1 — Web | W4. Core loop on web | OCR upload. /upload-trade with a real broker screenshot (NOT EURUSD) | extracted pair/entry/exit/P&L match the image — never the generic EURUSD / 0.01 lot / +50 sample. Then upload a blurry/non-chart image → clear "could not extract" error, no invented trade.
23 | Pass 1 — Web | W4. Core loop on web | Free-trade limit. On a free account log a 3rd trade in one market | limit dialog ("You've used your 2 free … trades"), and it opens the Razorpay paywall. Switch market → that market still allows its own 2 trades. Existing trades still viewable/editable.
24 | Pass 1 — Web | W4. Core loop on web | Dashboard reflects trades | P&L / trade count match what you logged; market switcher changes the numbers; no stale data after adding a trade.
25 | Pass 1 — Web | W4. Core loop on web | Checklist image preview | Checklist → expand a setup with reference images → click a thumbnail → the × close button is visible top-right and closes it. Also check at a short window height (reported bug).
26 | Pass 1 — Web | W4. Core loop on web | Phone width once | Resize the browser to ~375px: Add Trade (both markets), the paywall, and the Help widget are usable — no cut-off buttons, no horizontal scroll.
Pass 1 — Web › W5. Support is reachable — your post-launch safety net
27 | Pass 1 — Web | W5. Support is reachable — your post-launch safety net | /support logged out in a private window | page renders with articles + contact options (this URL goes to Google/Apple reviewers).
28 | Pass 1 — Web | W5. Support is reachable — your post-launch safety net | Open a ticket as a user from /support/tickets/new with a screenshot | appears in /admin/support within seconds; the attachment opens for the admin; pasting the raw image URL in a logged-out window returns 404 (private).
29 | Pass 1 — Web | W5. Support is reachable — your post-launch safety net | Report an issue from the app. OCR review screen → "Report OCR Issue" → submit with a screenshot | success screen shows a ticket code (EC-…); the ticket has a Bug report badge in /support/tickets and in /admin/support; the admin context panel shows the OCR values table.
30 | Pass 1 — Web | W5. Support is reachable — your post-launch safety net | Admin reply → user. Reply from /admin/support | user receives the notification/email and sees the reply on the ticket.
31 | Pass 1 — Web | W5. Support is reachable — your post-launch safety net | Issue → ticket sync. In /admin/issues, mark that report Fixed with a summary | the ticket gets a Support reply with the summary and becomes Resolved.
32 | Pass 1 — Web | W5. Support is reachable — your post-launch safety net | Floating Help widget opens on the dashboard, answers a question or hands off to "Create a support ticket"; WhatsApp / email links open with the correct number/address.
Pass 1 — Web › W6. Admin sanity
33 | Pass 1 — Web | W6. Admin sanity | /admin/users shows the accounts you just created with the correct plan; /admin/trades shows the trades you logged (including Setup / SL / TP fields); /admin/payments shows the real payment from W3.
34 | Pass 1 — Web | W6. Admin sanity | /admin/promotions — if launching with a coupon, it is active and tied to an active campaign.
Pass 2 — Android › A1. Store compliance — suspension risk
35 | Pass 2 — Android | A1. Store compliance — suspension risk | Build flags | The Android build was made with NEXT_PUBLIC_PAYMENTS_ENABLED=false and NEXT_PUBLIC_PLAY_BILLING_ENABLED=true.
36 | Pass 2 — Android | A1. Store compliance — suspension risk | No Razorpay on Android. Hit the free-trade limit in the app | the Google Play paywall opens. Razorpay UI must never appear anywhere in the app — also check Settings → Upgrade.
37 | Pass 2 — Android | A1. Store compliance — suspension risk | Play Console products match code | Subscription product ID and base plan IDs (edgecipline-pro-monthly, -3month, -6month) match backend/constants/googlePlay.js exactly; prices in the paywall are Play's own localized prices.
38 | Pass 2 — Android | A1. Store compliance — suspension risk | Store listing | Support URL and privacy policy URL open; listing screenshots show the current (redesigned) UI.
Pass 2 — Android › A2. Google Play money
39 | Pass 2 — Android | A2. Google Play money | Real purchase. With a license-tester account, subscribe from the paywall | Play sheet opens; after paying, Premium unlocks and the celebration screen shows the expiry.
40 | Pass 2 — Android | A2. Google Play money | Cancel out of the Play sheet | paywall returns to normal, no error, no charge.
41 | Pass 2 — Android | A2. Google Play money | Double-tap Subscribe | only one Play sheet opens.
42 | Pass 2 — Android | A2. Google Play money | Kill the app mid-purchase (after the Play sheet, before confirmation) → reopen | purchase is picked up and Premium is granted automatically.
43 | Pass 2 — Android | A2. Google Play money | Restore purchases. Uninstall/reinstall (or log out/in) → Restore | Premium restored without paying again. With no purchase on the device → "No previous Google Play subscription was found".
44 | Pass 2 — Android | A2. Google Play money | Cancel from Play Store. Play Store → Subscriptions → cancel the test sub | within a few minutes the app reflects it and /admin/payments shows the change (webhook path works).
Pass 2 — Android › A3. App-only behaviour
45 | Pass 2 — Android | A3. App-only behaviour | Login + session on the app; app kill and reopen keeps you logged in.
46 | Pass 2 — Android | A3. App-only behaviour | Push notifications | Trigger one (e.g. admin replies to your ticket) → notification arrives on the device and opens the right screen.
47 | Pass 2 — Android | A3. App-only behaviour | Camera / gallery | Add Trade → screenshot picker works; Report Issue → attaching from gallery works (Android storage permission prompt behaves).
48 | Pass 2 — Android | A3. App-only behaviour | OCR upload from the app with a real broker screenshot → correct extraction (not the EURUSD sample).
49 | Pass 2 — Android | A3. App-only behaviour | Checklist image preview on the phone (and in split-screen if you can) → the × button is visible and closes it.
50 | Pass 2 — Android | A3. App-only behaviour | Bug report from the app → ticket appears in /admin/support with platform = android and the app version shown.
51 | Pass 2 — Android | A3. App-only behaviour | Back button / bottom nav | Android back closes modals (paywall, image preview, Help widget) before leaving the screen; bottom nav works on both markets.
Final › Before deploy
52 | Final | Before deploy | Rollback noted: previous build / git tag written here: ______________ and you know the exact command to redeploy it.
53 | Final | Before deploy | Monitoring: you know where errors show up (logs / /admin/monitoring) and you will watch /admin/support + /admin/issues for the first 24 hours — the in-app reporter is now your live test suite.
54 | Final | Before deploy | Someone else (not the developer) has done W4 once, end to end, without help.